# Desk Assistant Robot

Complete build roadmap: V1 MVP → V2 → V3 → V4 autonomy

Raspberry Pi 4 • Differential drive • Pi Camera • HC-SR04 + IR • ROS 2 / Nav2 later • Local AI + APIs

Core design rule: AI may decide what the robot should try to do, but a deterministic safety layer always decides whether motion is allowed. Desk-edge detection and emergency stop must not depend on an LLM.

# 1. Recommended overall strategy

Build the robot as a differential-drive platform: two driven wheels plus a passive caster/ball.

Use the Raspberry Pi for high-level control, camera, perception, APIs, UI and later ROS 2 / Nav2.

At the encoder stage, keep motor PWM + encoder PID on the Raspberry Pi for this build. Use independent control/safety loops and a watchdog; move to a dedicated MCU only if measurements show the Pi is a bottleneck.

Use the available HC-SR04 ultrasonic sensors for obstacle proximity and the available IR sensors for desk-edge detection. The Pi Camera handles semantic object detection; these deterministic sensors remain the hard safety layer.

Use ROS 2 once the project has multiple sensor/control processes. Do not add ROS 2 to the first GPIO prototype just for the sake of using it.

Use Gazebo + RViz2 before V4 path planning. Use Nav2 for V4 rather than writing a complete navigation stack yourself.

Keep the AI boundary narrow: voice/text → structured command JSON; perception → detections; planner → safe motion goals. Every command is revalidated locally.

# 2. Target architecture

User → Terminal / Voice
          ↓
   Command Parser / LLM
          ↓
     Command Validator
          ↓
       Safety Supervisor  ← Pi Camera + HC-SR04 + IR + E-stop
          ↓
      Motion Controller
          ↓
      Raspberry Pi GPIO / Motor PWM
          ↓
         L298N → Motors

Camera → OpenCV / YOLO → object detections → Local state / Safety
Mic → whisper.cpp → text → LLM API → JSON commands + reply + emotion
LLM emotion → local emotion state machine → screen + voice + arm animations

V4 adds:
Perception → object goal → Nav2 planner/controller → safety supervisor → Raspberry Pi motor control

# 3. Master hardware + software table

Use this as the buying checklist: The motor voltage/current and battery must be chosen together. The exact motor driver is only final after checking motor stall current. The example parts below are practical defaults, not mandatory brands.

| # | Component | Qty | Purpose | Stage | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Raspberry Pi 4 Model B | 1 | Main computer; GPIO motor control, camera, CV, UI, APIs and later ROS 2 | V1–V4 | Locked choice for this build; no ESP32 is required. |
| 2 | microSD 64–128 GB, high-endurance | 1 | OS + logs | V1–V4 | SSD/USB 3 storage is better for heavy rosbag logging. |
| 3 | Pi Camera Module 3 | 1 | RGB camera | V1–V4 | Keep this camera for the final build. Use Picamera2/libcamera. |
| 4 | N20 metal gearmotor with quadrature encoder, 6 V, ~100–150 RPM | 2 | Drive wheels | V1–V4 | Pick a model whose stall current is safe for the motor driver. Target slow, controllable desk speed rather than car-like speed. |
| 5 | 60–65 mm rubber wheels | 2 | Drive wheels | V1–V4 | Smaller wheels make precise desk movement easier. |
| 6 | Ball caster / mini swivel caster | 1 | Third contact point | V1–V4 | Keep the robot footprint compact and low. |
| 7 | L298N / L298-2 Motor Board | 1 | 2 DC motor H-bridge | V1–V4 | Use the lab board. Expect more heat/voltage loss than a modern driver; keep speed modest. |
| 8 | Raspberry Pi GPIO + PWM | 1 | Motor PWM/control and later encoder/PID interface | V1–V4 | Pi is the only computer/controller for this build; keep safety/control loops lightweight and independent. |
| 9 | MPU6050 IMU breakout | 1 | Turn-angle feedback / orientation | Stage 3–V4 | Inventory part; use first. Better IMU is optional. |
| 10 | HC-SR04 ultrasonic sensors | 2–3 | Front/side obstacle distance | Stage 6 onward | Use lab HC-SR04 instead of buying ToF for the MVP. It is larger/slower but preserves proximity-stop functionality. |
| 11 | IR sensors | 3 | Desk-edge detection | Stage 10 onward | Inventory replacement for downward ToF; use as deterministic hard-stop sensors. |
| 12 | 3D-printed custom body | 1 | Houses electronics | Stage 2 onward | Locked choice. Design around the Pi, L298N, battery, Pi Camera and sensors. |
| 13 | 5 V / 5 A buck converter for Pi | 1 | Stable Pi power | All physical builds | Use a dedicated regulator; do not power motors/servos from Pi 5V. |
| 14 | 5–6 V buck converter for servos | 1 | Arm power | V2 onward | Size to servo stall current. |
| 15 | Protected 2S battery pack + fuse + master switch | 1 | Robot power | All physical builds | Exact capacity depends on desired runtime/current. Add fuse close to the battery. |
| 16 | USB microphone | 1 | Voice input | V2 onward | Start with USB for simplicity; integrate an I2S/PDM mic later only if needed. |
| 17 | Small powered speaker / USB speaker | 1 | Voice output | V2 onward | Fastest prototype path. For final compact build, use MAX98357A I2S amp + small speaker. |
| 18 | 2.0–2.4 in SPI TFT (ST7789/ILI9341 class) | 1 | Eyes / face | V2 onward | Drive with Pygame/Pillow/OpenCV-style framebuffer rendering. |
| 19 | PCA9685 16-channel servo driver | 1 | Arm servos | V2 onward | Offloads stable servo PWM from Pi; useful once arms exist. |
| 20 | Micro servos, SG90/MG90S class | 2–4+ | Arm joints | V2 onward | Quantity depends on arm design. MG90S is the safer default for small mechanical loads. |
| 21 | M3 brass heat-set inserts + M3 screws/standoffs | assorted | Mechanical assembly | Stage 2 onward | Makes the body serviceable instead of gluing everything together. |
| 22 | Emergency-stop switch + normally-open/closed safety wiring | 1 | Hard safety | V1 onward | Wire so the drive power is removed or motor-enable is disabled by default on fault. |

## 3.1 ECE357 inventory: what you already have

The uploaded ECE357 Components List 2026 contains several parts that can cover early prototypes. The table below distinguishes direct-use parts from substitutes and missing parts so you do not buy things you already have.

| Build need | Inventory item(s) | Qty in list | How to use it | Decision |
| --- | --- | --- | --- | --- |
| Raspberry Pi | Raspberry Pi-4 B / Model B | 20 | Use as the only main computer/controller for V1–V4. | USE |
| Motor driver | L298-2-Motor Board / L298N | 26 | Use for all prototype and MVP motor control. | USE |
| Motor control / PWM | Raspberry Pi 4 B | 20 | Use Pi GPIO/PWM directly; Arduino UNO remains optional for bench experiments, not required by the build. | USE PI |
| IMU | MPU6050 | 40 | Use for rough yaw/turn feedback. | USE |
| Obstacle range | Ultrasonic HCRS04 / HC-SR04 | 112 | Use as the MVP proximity sensor instead of ToF. | USE |
| Desk-edge sensing | IR Sensor | 180 | Use 3 downward-facing sensors as the deterministic edge detector. | USE |
| Camera | Pi Camera Module 3 | KEEP | Keep the Pi Camera as the chosen final camera; Picamera2/libcamera. | KEEP |
| Face/eyes display | TFT-Touch 2.4 SPFD5408 | 5 | Use for V2 animated eyes. | USE |
| Arm actuators | Servo Motor listed as 996R, 9g | 30 | Use for small arm joints where torque is sufficient. | USE |

## 3.2 What to buy vs. reuse

This is the practical purchase plan after reconciling the lab inventory. Prototype with the substitutions where useful, but keep the final architecture modular so the components can be swapped without rewriting the Robot API.

| Needed for final robot | Inventory status | Recommended action | Why |
| --- | --- | --- | --- |
| 2 geared DC drive motors with quadrature encoders | NOT LISTED | BUY LATER: 2× N20-class geared encoder motors | Needed for repeatable distance/turn control; this is the one major V1 upgrade that cannot be replaced cleanly by an existing lab part. |
| Pi Camera Module 3 | USER-REQUIRED / KEEP | KEEP | Use the Pi Camera as requested; do not substitute with the lab OV7670. |
| 3D-printed custom body | USER-REQUIRED / KEEP | KEEP | Use the custom printed body; design around actual components after motor selection. |
| Battery + Pi power regulator + fuse + master switch | NOT LISTED | BUY | Required for a safe untethered robot. Size battery and motor power together. |
| Physical E-stop / motor-enable cutoff | NOT LISTED | BUY BEFORE FINAL DESK TESTS | Software E-stop is okay for bench work; use a physical cutoff for the moving desk robot. |
| USB microphone + speaker | NOT LISTED | BUY IN V2 | Required for voice I/O. The lab sound sensor is not a speech microphone. |
| Servo driver (PCA9685) | NOT LISTED | OPTIONAL V2 | Useful when multiple arm servos are active; direct Pi servo control can prototype one or two servos. |
| Better IMU (BNO085/BNO086) | NOT LISTED | DO NOT BUY FOR MVP | Use the inventory MPU6050. Upgrade only if turn accuracy proves inadequate. |
| ToF sensors / TCA9548A | NOT LISTED | DO NOT BUY FOR MVP | Use HC-SR04 for object proximity and IR sensors for desk-edge detection. True per-pixel depth remains a later upgrade/shortcut. |
| TB6612FNG / ESP32 | NOT LISTED | DO NOT BUY | The chosen build uses the Raspberry Pi + L298N directly. |

# 4. Master software/tool table

| Tool | Use | Stage | Why / shortcut |
| --- | --- | --- | --- |
| Python 3 | Main Pi code, motor control, safety and orchestration | V1–V4 | Simple ecosystem for GPIO, CV, APIs and orchestration. |
| gpiozero | Easy Pi motor/GPIO control | V1–V4 | Fastest way to prototype GPIO motor control on the Pi; use the backend supported by your Pi OS. |
| lgpio / native GPIO interface | Lower-level GPIO | V1+ | Use only if gpiozero introduces a measured limitation; do not optimize prematurely. |
| argparse / Typer | Terminal CLI | V1–V3 | argparse = zero extra dependency; Typer = nicer command-line UX. |
| NumPy | Control/math | V1–V4 | Geometry, encoder math, filtering, depth calculations. |
| OpenCV | Camera + image processing | V1-6 onward | Capture, drawing boxes, calibration, image transforms. |
| Picamera2/libcamera | Pi Camera access | V2–V4 | Preferred path for Raspberry Pi camera modules. |
| Ultralytics YOLO | Object detection/tracking | Stage 6+ | Use a small/nano model. Current Ultralytics docs expose Python + CLI workflows and export to ONNX. |
| OpenCV ArUco / AprilTag-style fiducials | Optional localization landmarks | V4 | Cheap way to establish a repeatable desk coordinate frame without full SLAM. |
| Whisper.cpp | Local speech-to-text | V2+ | Offline ASR that explicitly supports Raspberry Pi. |
| Piper TTS | Local text-to-speech | V2+ | Fast local TTS; use a voice model whose license fits your use. |
| FFmpeg | Chipmunk audio effect | V2 | Simple, scriptable audio resampling/pitch effect. |
| Pygame / Pillow | Eyes + animations | V2 | Simple 2D animation stack. |
| Pydantic | Validate LLM JSON | V2+ | Convert JSON Schema / model definitions into robust validation at the command boundary. |
| Gemini API structured output | LLM → JSON commands | V2 | Use JSON Schema / Pydantic rather than free-form parsing. |
| asyncio + multiprocessing | Independent loops | V2 | Use processes for expensive CV/AI work; async for I/O. Avoid one giant blocking loop. |
| ROS 2 Jazzy | Robot middleware | Recommended from Stage 5/6 onward | Use nodes/topics/services/actions/TF2 once the system becomes multi-process. |
| TF2 | Coordinate frames | ROS 2 / V4 | Transforms camera/sensor/robot/map coordinates consistently. |
| rosbag2 | Record/replay | ROS 2 / V3+ | Capture sensor/command data for debugging without re-driving the robot. |
| RViz2 | Robot visualization | ROS 2 / V4 | Inspect robot pose, TF, sensor data and paths. |
| Gazebo Harmonic | Simulation | ROS 2 / V4 prep | Use with ROS 2 Jazzy; official Gazebo docs recommend Ubuntu 24.04 + Jazzy + Harmonic for new users. |
| Nav2 | Path planning + navigation | V4 | Best shortcut for planners, controllers, costmaps, localization interfaces and behavior trees. |
| Foxglove | Robotics telemetry dashboard | V3+ | Much faster than building a custom telemetry UI from scratch; supports live ROS 2 and recorded MCAP workflows. |
| PlatformIO | Not required for chosen Pi-only architecture | — | Keep in mind only as a future MCU option; not part of this build. |
| librespot | Spotify Connect receiver | V3 | Open-source Spotify Connect client; requires Spotify Premium. Alternative is Spotify Web API for playback control. |
| React + Vite + Tailwind/shadcn-style component library | Custom dashboard | V3 | Use only after Foxglove proves insufficient; keeps your custom UI polished. |
| systemd | Boot-time services/watchdogs | V3 | Start robot processes automatically and restart failed services. |
| Git + GitHub | Version control | V1–V4 | Use separate commits/releases for each working stage. |
| pytest | Automated tests | V1–V4 | Test command parsing, safety decisions, geometry, and state transitions without hardware. |

# 5. Before Stage 1: set up the project correctly

Use Git from day 1. Never work directly in one giant Python file.

Keep hardware access isolated from control logic so you can simulate/test control code on a laptop.

Create a config file for wheel diameter, wheelbase, GPIO pins, motor inversion, speed limits and safety thresholds.

Use a physical emergency-stop / motor-enable disable before putting wheels on the floor/desk.

desk-robot/
├── robot/
│   ├── api.py                 # robot.forward(20), robot.turn_left(90)
│   ├── state.py               # shared local state
│   └── config.py
├── hardware/
│   ├── motors.py
│   ├── encoders.py
│   ├── tof.py
│   ├── imu.py
│   ├── camera.py
│   └── audio.py
├── control/
│   ├── pid.py
│   ├── differential_drive.py
│   └── motion_controller.py
├── safety/
│   ├── supervisor.py
│   ├── obstacle_guard.py
│   └── edge_guard.py
├── perception/
│   ├── detector.py
│   ├── depth.py
│   └── gestures.py
├── behavior/
│   ├── emotions.py
│   ├── animations.py
│   └── choreography.py
├── llm/
│   ├── client.py
│   ├── schema.py
│   └── prompts.py
├── cli.py
└── main.py

# V1 MVP

Goal: A fast desk-safe robot that accepts direct commands, detects obstacles/edges, stops, slows/speeds, and redirects around objects.

| Stage | Goal | Components / implementation | Implementation | Shortcut | Better way | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| V1-1 | Motor control: forward/back/left/right/stop | Raspberry Pi 4 B + L298N + 2 DC geared motors; Python + gpiozero. API: robot.forward(20), robot.stop(). | Start with a Python class wrapping the driver. Keep all GPIO code inside hardware/motors.py. | Use the lab Pi 4 + L298N. No ESP32/Arduino is needed. | Keep the hardware abstraction clean so a better motor driver can be swapped in later without changing Robot API. | Each direction works reliably at low speed; stop is instant. |
| V1-2 | Make the body | 3D printed chassis; target ~180×140×80 mm, adjustable after motor/wheel choice. | Design around serviceability: removable top, battery low, camera mast separate, sensor cutouts, vents. | Fusion 360 or FreeCAD; export STL/3MF. Print a cheap chassis first before the final shell. | Make the chassis around the electronics, wheel geometry and sensor FOV, not the other way around. | All components fit without cable strain; battery and Pi accessible. |
| V1-3 | Turn X degrees | MPU6050 (inventory) for yaw feedback. Implement robot.turn_left(90) / turn_right(90). | A timed turn is only approximate. With the MPU6050, estimate yaw and stop when the target angle is reached, with drift/limits handled explicitly. | Use the available MPU6050 instead of buying a better IMU. | Later combine encoder feedback + IMU for repeatable heading; do not call timed turns exact. | Repeated turns are within your chosen tolerance under normal conditions. |
| V1-4 | Unified command: type, amount, speed | API: robot.move(type="forward", amount=20, unit="cm", speed=0.5). | Use one command representation internally even if CLI syntax differs. Normalize speed to 0..1. | Typer gives a clean CLI; Pydantic can validate command objects later when LLM is added. | Better: include acceleration/deceleration limits now, not later; avoid instant full PWM jumps. | All movement commands accept type + amount + speed and obey max-speed limits. |
| V1-5 | Encoder | Buy 2 geared encoder motors when you reach this stage. Keep Raspberry Pi as the controller; read encoder pulses on Pi GPIO and close the wheel PID loop there. | Track ticks, wheel velocity, distance and yaw estimate. Use separate control and safety loops. | Do not wait for a dedicated MCU; prototype encoder handling directly on the Pi. | If measurements later show GPIO timing/CPU contention, add a microcontroller only as an optimization—not as a required architecture change. | Known-distance moves are repeatable; left/right motor mismatch is corrected. |
| V1-6 | Camera + range sensors + bounding boxes | Pi Camera Module 3 + HC-SR04 ultrasonic sensors + IR edge sensors + YOLO/OpenCV. | YOLO returns boxes/classes; range sensors provide metric proximity. Keep sensor access separate from the detector. | Use the Pi Camera you selected; use lab HC-SR04 for proximity and IR for the edge layer. | Keep camera, ranging and safety as separate modules so ToF can be added later without rewriting the pipeline. | Boxes are drawn and objects are classified at a useful local frame rate. |
| V1-7 | Depth perception | Practical MVP depth = RGB bounding-box geometry + HC-SR04 range association; optional monocular depth model only as an experiment. | Calibrate camera-to-robot and place the HC-SR04 so its range corresponds to the forward obstacle region. Treat range as approximate. | You can avoid ToF for the MVP; use ultrasonic distance for “how far is the obstacle?” and camera boxes for “what is it?” | For true per-pixel depth, add a stereo/depth camera later; do not make a heavy depth model a safety dependency on the Pi. | For a detected obstacle, system can estimate “distance from robot” in cm with known error bounds. |
| V1-8 | Print object detected | Terminal logger consumes detection events. Example: [VISION] cup detected x=..., z=... | Debounce repeated detections so the terminal is useful instead of printing 30 identical lines/sec. | Python logging module; later publish a ROS topic. | Better: log structured JSON internally and render friendly text at the CLI/dashboard. | Object event appears once when entering detection state and optionally on meaningful updates. |
| V1-9 | Stop if object is close | HC-SR04 inventory sensors + safety supervisor. | Set HARD_STOP_DISTANCE and CAUTION_DISTANCE. At hard stop, command zero immediately. | Start with one front sensor; add left/right coverage only when redirect behavior is implemented. | Hard-stop decisions should be deterministic and independent of YOLO/LLM. | Robot stops inside the configured safety margin in repeated tests. |
| V1-10 | Detect desk edge + stop + message | IR sensors (inventory, Qty 180) as downward desk-edge sensors. | Place 3 downward sensors near the front footprint. Treat loss of desk return / abnormal reading as an edge fault. | Use the abundant IR sensors and 3D-print a protected sensor bracket. | Keep camera-based edge detection supplementary; IR remains the hard stop. | Robot stops before wheels cross the edge in repeated tests. |
| V1-11 | Slow down / speed up accordingly | Distance-based speed controller + acceleration ramp. | Example logic: far=cruise; medium=slow; close=stop. Apply slew-rate limiting to PWM/velocity. | NumPy is enough; PID belongs at wheel level, not here. | Better: control desired linear/angular velocity, not raw PWM, once encoders exist. | Approach speed is smooth and does not oscillate near objects. |
| V1-12 | Real object vs marking | RGB + HC-SR04 range association + desk-plane reasoning; optional future stereo depth. | Use the camera to identify objects and ultrasonic range to estimate obstacle distance. For markings vs objects, combine box shape, temporal consistency and whether the detected region rises above the known desk plane. | Avoid ToF for the MVP; the HC-SR04 preserves the key obstacle-depth signal needed by the safety logic. | For stronger 3D discrimination later, add a stereo/depth camera rather than making a heavy monocular model a safety dependency. | Printed/painted markings are rejected reliably in your lighting setup; physical objects are retained. |
| V1-13 | Redirect around object; stop at edge | Local reactive obstacle avoidance; edge has higher priority than obstacle redirect. | If object blocks front, sample left/right clearance; choose the safer free side; turn/advance; re-check. If edge risk occurs, STOP/retreat and turn away. | A simple rule-based controller is enough for the MVP. | Do not implement Nav2 yet. On a small fixed desk, a reactive controller is simpler and lower latency. | Object causes a safe detour; desk-edge event always wins over redirect. |

V1 MVP boundary: Stop here before adding voice/AI. You should be able to manually drive the robot around the desk, place arbitrary objects in front of it, and repeatedly verify: object → slow/stop/redirect; edge → hard stop; sensor failure/stale data → safe stop.

# 6. V1 key algorithms / logic

## 6.1 Command API

robot.forward(20)
robot.backward(10, speed=0.35)
robot.turn_left(90, speed=0.25)
robot.turn_right(45, speed=0.20)
robot.stop()

# Normalized internal command
Command(type="forward", amount=20, unit="cm", speed=0.5)

## 6.2 Safety priority

Priority order:
1. Emergency stop / motor watchdog
2. Desk-edge hazard
3. Sensor failure / stale data
4. Immediate collision hazard
5. Medium-range obstacle
6. Normal movement

The winner controls the final motor command. No higher layer can override a lower-level safety stop.

## 6.3 Object avoidance

front blocked?
  ├─ edge risk? → STOP / retreat / turn away
  └─ object only?
       ├─ check left clearance
       ├─ check right clearance
       └─ choose safer side → slow turn → re-check → continue

## 6.4 Speed profile

distance_to_obstacle > caution_distance → cruise_speed
caution_distance >= d > hard_stop_distance → speed = scaled_down(d)
d <= hard_stop_distance → speed = 0

Always also enforce an acceleration/deceleration limit so speed changes are smooth.

# V2: Voice + personality + arms + local state

| Stage | Goal | Tools | Implementation | Shortcut | Better way | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| V2-1 | Microphone + speech-to-text | USB mic + whisper.cpp | Push-to-talk first. Keep wake-word as a later option. | whisper.cpp explicitly supports Raspberry Pi and can run offline. | For lowest latency, keep the speech recognizer local and use a small model appropriate for the Pi. | Speech becomes text on-device. |
| V2-2 | LLM API → JSON command + text | Gemini API structured output + Pydantic schema | Use JSON Schema; never parse “almost JSON” with regex. | Gemini supports schema-constrained structured outputs and Pydantic/Zod integration. | Better: expose only a tiny allow-list of robot functions; reject all unknown fields/commands locally. | Every voice utterance becomes validated command JSON + response text. |
| V2-3 | Speaker + separate spoken output | USB speaker first; later MAX98357A I2S amp + speaker; Piper TTS | Create a speech queue so speaking never blocks motion/safety loops. | Piper gives local TTS; keep audio generation asynchronous. | Separate “terminal reply” from “spoken reply” in the LLM schema. | Robot speaks without delaying motion/safety. |
| V2-4 | Chipmunk effect | FFmpeg or a lightweight DSP step | Pitch-shift after TTS; cache common phrases if used repeatedly. | FFmpeg is simpler than introducing a large audio stack. | Better: pre-generate/cache common responses and only synthesize dynamic speech. | Speech has the desired voice effect with acceptable latency. |
| V2-5 | Eyes on screen | 2.0–2.4 in SPI TFT (inventory has TFT-Touch 2.4 SPFD5408 x5) + Pygame/Pillow | Use the available TFT first. Render a fixed 2D eye/face scene and keep animation independent from control loops. | Inventory TFT is the quickest way to prototype the eyes. | 30-ish FPS face animation without blocking robot control. |  |
| V2-6 | LLM emotional state output | Extend JSON with emotion enum | Example enum: idle, happy, curious, excited, worried, sad, confused, angry. | Validate against enum locally. | Better: LLM suggests emotion, but local events can override it; e.g., edge hazard → worried/alert. | One canonical current emotion exists in local state. |
| V2-7 | Hardcoded animation per emotion | Animation assets + emotion map | Store animation metadata in JSON/YAML; code only executes clips. | Separate assets from logic so you can add art without changing code. | Emotion maps cleanly to an animation clip. |  |
| V2-8 | Multiple animations + random idle | Scheduler + random.choice over an asset manifest | Use cooldowns/weights to prevent the same animation repeating constantly. | Better: weighted random + cooldown + interruption rules (speech/movement/emergency can interrupt idle). | Idle feels alive but never overrides important states. |  |
| V2-9 | Confusion state | Schema validation + ambiguity check | Set confusion when command is missing/ambiguous or confidence is low. | Better: LLM returns `needs_clarification: true` rather than inventing a command. | Unclear inputs produce a safe clarification response, never a guessed motion. |  |
| V2-10 | Arm command | Inventory servo motors + Raspberry Pi PWM for early prototype; PCA9685 optional when many joints are active. | Use named arm poses/animations rather than raw servo angles in the command layer. | Start with one or two servos directly from the Pi; add PCA9685 when channel count grows. | Arm commands execute independently but still go through safety/state rules. |  |
| V2-11 | Emotion → arm animation | Local mapping from emotion to named choreography | Never ask the LLM for raw servo angles during normal operation. | Use named safe poses + local command sequences. | Emotion changes can trigger a safe arm clip. |  |
| V2-12 | Continuously updated local state | Python dataclass/Pydantic model + monotonic timestamps | State contains motion, pose, sensors, current command, speech, emotion, arms, errors. | If using ROS 2, publish a read-only state topic in parallel. | One state object can answer “what is the robot doing right now?” at any moment. |  |
| V2-13 | Independent loops | Separate processes + ROS 2 when integrated; asyncio/queues for I/O. | Keep safety/motor control, perception, speech, animation and command/LLM work independent. | The Pi is the single computer; isolate heavy CV/AI work so it cannot stall the safety loop. | A single Pi can satisfy the MVP/V2 requirement when loops are bounded, timestamped and independently scheduled. |  |

Recommended LLM response shape
{
  "say": "Okay, moving forward.",
  "emotion": "happy",
  "needs_clarification": false,
  "commands": [
    {
      "type": "forward",
      "amount": 20,
      "unit": "cm",
      "speed": 0.45
    }
  ]
}

Local validator then checks:
- command type is allow-listed
- unit is cm or degrees
- amount is within max bounds
- speed is 0..1
- safety permits motion

# V3: Perception-driven interaction + robustness + dashboard + music + plugins

| Stage | Goal | Tools | Implementation | Shortcut | Better way | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| V3-1 | Detect user actions (waving etc.) | MediaPipe hand/gesture recognition or custom OpenCV detector | Add only the event/label to the LLM context: `USER_WAVED`, not the whole video stream. | MediaPipe is a strong shortcut for hand/gesture primitives; use temporal smoothing to avoid one-frame false positives. | Better: a small finite state/event layer converts vision into stable events before the LLM sees them. | Reliable gesture events are available to command/behavior layer. |
| V3-2 | Emergency states + backups | Safety supervisor + heartbeat + watchdog + physical E-stop (not listed in inventory) | States: NORMAL, CAUTION, STOPPED, EDGE_HAZARD, SENSOR_FAULT, E_STOP, LOW_BATTERY. Add a physical motor-enable cutoff. | systemd can restart crashed processes; MCU heartbeat can disable motors if Pi stops responding. | Use a Pi watchdog/systemd and hardware E-stop. Do not make an MCU heartbeat mandatory for this build. | Unplugging/killing a process causes a safe state instead of uncontrolled motion. |
| V3-3 | Beautiful dashboard | Foxglove first; custom React only where needed | Use Foxglove for telemetry and debugging before building a custom dashboard. | Foxglove can connect to live ROS 2 data and open recorded MCAP data. | Better: custom UI reads from a local WebSocket/API while ROS 2 remains the internal robotics bus. | You can see camera, detections, state, speed, commands, sensors, logs. |
| V3-4 | Spotify | Spotify Web API / Web Playback SDK or librespot | For a prototype, use librespot as a Spotify Connect receiver. | librespot can act as a Connect receiver but requires Spotify Premium. Spotify’s official Web API also requires Premium for playback control. | Keep this integration isolated behind `music.play()/pause()/next()` so the robot does not depend on Spotify internals. | Robot can start/pause/select music without touching safety/control. |
| V3-5 | Completely local apart from APIs | Local STT + local TTS + local CV + local dashboard + optional remote LLM API | Keep all raw audio/video/sensor streams on LAN/device unless an API call is explicitly required. | Use API keys only in local environment variables and never commit them. | Better: default-deny networking; make remote calls explicit and observable. | Robot remains functional for movement/CV/voice feedback if the cloud LLM is unavailable, except for cloud-dependent intent understanding. |
| V3-6 | Choreographed dance Python file | Python plugin interface + safe Robot API | Example plugin: `def dance(robot): robot.forward(...); robot.turn_left(...); robot.arm(...)`. | Run choreography in a sandbox-like subprocess with a restricted Robot API; do not let plugins access GPIO directly. | Better: compile/validate choreography into an allow-listed command sequence before execution; include dry-run mode. | Drop-in choreography files can be run safely without bypassing the safety layer. |

# V4: “Find object B and navigate to it”

Target behavior: The robot receives an object goal such as “go to object B”, searches by rotating if the object is not visible, estimates a goal location, plans a collision-safe path, and drives there without crossing the desk boundary.

V4 behavior

1. Receive goal: object="B"
2. Search: inspect current camera view
3. If not found: rotate in controlled increments (or full 360° scan)
4. Detect object B + estimate depth/position
5. Project target into robot/world coordinates
6. Build/update local costmap
7. Nav2 planner → safe path
8. Nav2 controller → velocity commands
9. Safety supervisor continuously vetoes edge/collision hazards
10. Stop at target approach distance
11. Report success / not found / blocked

| Stage | Goal | Recommended implementation | Shortcut | Better way |
| --- | --- | --- | --- | --- |
| V4-1 | Target search | YOLO object detection + camera + depth/ToF | Rotate 30–60° per scan step; continue until object is detected or 360° has been covered. | Use a target-tracking state, not one-frame detection. Require several consistent frames. |
| V4-2 | Desk coordinate system | Wheel odom + IMU; optional AprilTag/Aruco landmarks | For one fixed desk, avoid full SLAM initially. Measure the desk and create a static map/boundary. | Add visual landmarks if odometry drift is too large. |
| V4-3 | Path planning | ROS 2 + Nav2 + costmaps | Use Nav2 planners/controllers instead of writing A* + local controller from scratch. | For a desk-sized environment, a 2D static occupancy map + dynamic obstacle layer is enough. |
| V4-4 | Desk boundary | Edge sensors + keepout map | Treat edge sensors as a hard veto even if Nav2 thinks an area is free. | Add a conservative keepout boundary inside the actual desk edge in the map. Nav2 costmaps support obstacle/keepout concepts; your hard edge sensor remains the final guard. |
| V4-5 | Object approach | Stop at a standoff distance | Once target is within a safe approach radius, stop navigation and optionally face the object. | Do not drive until the bounding box fills the camera; keep a configurable approach distance. |

Why Nav2 belongs here: V4 is the first requirement that genuinely benefits from a navigation framework. Nav2 provides planners, controllers, costmaps, state-estimation interfaces and behavior-tree orchestration, so you can spend time on your object-search behavior instead of rebuilding the navigation stack.

# 8. Where ROS 2 should enter the project

| Stage | ROS 2? | Recommendation |
| --- | --- | --- |
| V1-1 to V1-4 | No | Plain Python is faster to prototype. Keep the Robot API ROS-ready. |
| V1-5 encoder | Optional | Use the ESP32 + serial protocol first. ROS 2 can consume encoder/odometry data later. |
| V1-6 / V1-7 | Recommended | Once camera + ToF + odometry exist, ROS 2 topics become useful for independent perception/control processes. |
| V1-8 onward | Recommended | Publish detections, state and sensor data. Use rosbag2 for logs. |
| V2 | Recommended | Run independent nodes/processes for command, perception, speech, audio, animation and safety. |
| V3 | Strongly recommended | Use ROS 2 as the internal robotics bus; Foxglove can visualize it. |
| V4 | Required/recommended | Use Nav2 + TF2 + costmaps + RViz2; Gazebo simulation should mirror the hardware interfaces. |

Suggested ROS 2 nodes

/motor_controller      → low-level velocity interface
/odometry              → /odom
/imu_node              → orientation
/range_node             → HC-SR04 range topics
/edge_node              → IR edge status
/camera_node           → /image_raw
/perception_node       → /detections
/safety_node           → safety state + final motion gate
/command_node          → user / LLM commands
/emotion_node          → emotion state
/audio_node            → STT/TTS
/animation_node        → screen + arm clips

Core topics/interfaces later:
/cmd_vel
/odom
/tf
/camera/image_raw
/detections
/robot_state
/safety_state

# 9. Simulation / development shortcuts

Gazebo Harmonic + ROS 2 Jazzy: use this once motion/odometry interfaces are stable. Gazebo’s official docs currently recommend Ubuntu 24.04 + ROS 2 Jazzy + Gazebo Harmonic for new users and document the `ros_gz` bridge.

RViz2: use it to inspect TF, robot pose, sensors and paths before debugging the physical robot.

Foxglove: use it before building a custom dashboard; it can visualize live ROS 2 data and recorded MCAP sessions.

rosbag2: record real robot runs and replay them while tuning perception/state logic.

Gazebo project template: start from the official `ros_gz_project_template` instead of hand-writing a ROS/Gazebo workspace structure for V4.

# 10. Low-latency / smoothness rules

Safety and motor control must not wait for LLM, speech or camera inference.

Keep encoder counting + wheel PID on the Raspberry Pi for this build; only add a dedicated MCU later if profiling proves the Pi is a bottleneck.

Run object detection at a lower rate than the HC-SR04/IR safety loop. A 5–15 FPS perception loop can coexist with a much faster deterministic sensor safety loop.

Use bounded queues. Never let 20 old commands wait while the robot executes stale intent.

Timestamp every sensor measurement. Reject stale data.

Use acceleration limits/slew rate. Smoothness comes from velocity control, not from sleeping after PWM writes.

Measure latency. Add timestamps for command_received, safety_decision, motor_command_sent, perception_frame, and actuator_feedback.

Cache repeated TTS/animation assets. Keep speech generation and playback off the control thread.

Use hardware watchdog/E-stop behavior so a crashed Python process cannot leave motors energized.

# 11. Safety test matrix before each major release

| Test | Setup | What to test | Pass condition |
| --- | --- | --- | --- |
| Motor test | Robot lifted off desk | Every motor direction, PWM range, inversion, stop | No unexpected movement. |
| Command bounds | Software-only | Zero, negative, very large, wrong unit, wrong type | Invalid command rejected. |
| Obstacle test | Object at increasing distances | Far / caution / hard-stop | Speed decreases smoothly, then stops. |
| Edge test | Place robot near desk edge with wheels clear | Approach slowly from multiple angles | Hard stop occurs before wheel crosses edge. |
| Sensor unplug | Disconnect ToF / camera / encoder | During idle and motion | System enters defined safe state. |
| Process crash | Kill perception / command / LLM process | During movement | Robot remains under safety control; motors stop if heartbeat expires. |
| Network loss | Disable Wi-Fi | During remote dashboard / LLM use | Movement safety remains local. |
| LLM nonsense | Feed malformed / unknown / huge command JSON | V2+ | Schema validation rejects it. |
| Plugin abuse | Choreography tries invalid command / GPIO | V3+ | Sandbox/API prevents safety bypass. |

# 12. Practical milestone checklist

| Milestone | Result | Stages | Acceptance test |
| --- | --- | --- | --- |
| M1 | Robot drives manually | V1-1 to V1-2 | Forward/back/left/right/stop; body assembled. |
| M2 | Robot turns predictably | V1-3 to V1-4 | Speed control + angle command; IMU preferred before encoders. |
| M3 | Robot has closed-loop movement | V1-5 | Encoders + PID; distance/turn repeatability. |
| M4 | Robot sees and ranges | V1-6 to V1-8 | Boxes + terminal events + distance. |
| M5 | Robot is desk-safe | V1-9 to V1-13 | Obstacle stop, edge stop, speed scaling, redirect. |
| M6 | Robot talks and has a face | V2-1 to V2-8 | STT → LLM JSON → action + voice + emotion animation. |
| M7 | Robot behaves like a product | V2-9 to V3-6 | State, watchdogs, gestures, dashboard, music, choreography. |
| M8 | Robot navigates to objects | V4 | Object search + goal pose + Nav2 + safety-supervised path. |

# 13. My exact recommended choices for this build

LOCKED INVENTORY-FIRST HARDWARE: Raspberry Pi 4 B + L298N + MPU6050 + HC-SR04 + IR sensors + Pi Camera + 3D-printed custom body + available servo motors. Buy later only for encoder motors, battery/power protection, physical E-stop, microphone/speaker and optional servo driver. No ESP32, TB6612FNG, BNO085/BNO086 or ToF is required for the planned MVP.

Software default: Python + gpiozero for V1, Picamera2/OpenCV for Pi Camera, Ultralytics YOLO for object detection, whisper.cpp for local STT, Gemini structured output + Pydantic for V2 command JSON, Piper TTS, FFmpeg for chipmunk effect, Pygame/Pillow for eyes, ROS 2 Jazzy + TF2 + rosbag2 + RViz2 from the multi-process stage, Gazebo Harmonic for simulation, Nav2 for V4, Foxglove for telemetry.

SHORTCUTS / REPLACEMENTS: Pi 4 replaces Pi 5 for this build; L298N replaces TB6612FNG; MPU6050 replaces BNO085/BNO086; HC-SR04 + IR replaces ToF for the MVP; Pi Camera remains the chosen camera; the 3D-printed custom body remains the chassis; Raspberry Pi replaces ESP32. OAK-D Lite remains an optional future depth shortcut only if true stereo depth becomes important. Foxglove can replace most of the first dashboard; Nav2 replaces most V4 navigation code.

# 14. Things not to do

Do not let an LLM directly output GPIO/PWM values.

Do not use cloud vision for collision safety.

Do not treat YOLO confidence as proof that something is physically real. Use geometry/depth/temporal evidence.

Do not power motors or servos from the Pi 5V rail.

Do not use a timed turn and call it “exact” without feedback.

Do not let idle animations, speech playback or dashboard rendering block the control/safety loop.

Do not let dance/choreography scripts access GPIO directly. Give them only the safe robot API.

Do not start V4 by writing your own full SLAM + global planner + local planner. Use Nav2 and add only the behavior unique to your robot.

# 15. Current reference links (verified October 6, 2026)

• Raspberry Pi 5 product / announcement — https://www.raspberrypi.com/news/introducing-raspberry-pi-5/

• Raspberry Pi Camera Module 3 — https://www.raspberrypi.com/products/camera-module-3/

• gpiozero Motor API — https://gpiozero.readthedocs.io/en/latest/api_output.html

• ROS 2 / Nav2 concepts — https://docs.nav2.org/jazzy/getting_started/navigation_concepts/

• Nav2 main documentation — https://docs.nav2.org/jazzy/

• Nav2 first-time robot setup — https://docs.nav2.org/jazzy/configuration_and_development/first_time_robot_setup_guide/

• Gazebo: ROS 2 + Gazebo version pairing — https://gazebosim.org/docs/harmonic/ros_installation/

• Gazebo ROS 2 integration — https://gazebosim.org/docs/harmonic/ros2_integration/

• Gazebo ROS project template — https://gazebosim.org/docs/harmonic/ros_gz_project_template_guide/

• Ultralytics YOLO Python usage — https://docs.ultralytics.com/usage/python

• Ultralytics quickstart / CLI — https://docs.ultralytics.com/quickstart

• Google Gemini structured outputs — https://ai.google.dev/gemini-api/docs/structured-output

• Whisper.cpp — https://github.com/ggml-org/whisper.cpp

• Piper TTS community repository — https://github.com/Piper-TTS-Speech-Synthesis/

• VL53L1X official ST page — https://www.st.com/en/imaging-and-photonics-solutions/vl53l1X.html

• TCA9548A I2C multiplexer guide — https://learn.adafruit.com/adafruit-tca9548a-1-to-8-i2c-multiplexer-breakout/overview

• Foxglove ROS 2 integration — https://docs.foxglove.dev/docs/getting-started/frameworks/ros2

• micro-ROS brochure — https://micro.ros.org/download/micro-ROS_Brochure.pdf

• PlatformIO ESP32 docs — https://docs.platformio.org/en/latest/platforms/espressif32.html

• Luxonis OAK-D Lite — https://docs.luxonis.com/hardware/products/OAK-D%20Lite

• Spotify Web API — https://developer.spotify.com/documentation/web-api

• Spotify Web Playback SDK — https://developer.spotify.com/documentation/web-playback-sdk

• librespot — https://github.com/librespot-org/librespot

# Appendix A — Full ECE357 Components List 2026

This appendix reproduces the supplied inventory and adds a roadmap relevance note. Quantities are exactly as provided in the spreadsheet, including the stepper-motor entry “5+10”.

| Sr. No. | Item Description | Model | Qty-Total | Roadmap relevance | Notes / recommended use |
| --- | --- | --- | --- | --- | --- |
| 1 | STM32F303RE |  | 95 | NOT NEEDED | Microcontroller; no need for V1–V4 if using Pi + ESP32/Arduino. |
| 2 | STM32L476RG |  | 14 | NOT NEEDED | Microcontroller; not required for this robot. |
| 3 | STM32F767ZI |  | 15 | NOT NEEDED | Microcontroller; not required for this robot. |
| 4 | Arduino-UNO | R3 | 112 | USE | Good for early encoder/motor-control experiments. |
| 5 | Raspberry Pi-2 | Pi2 Model B | 2 | NOT RECOMMENDED | Too limited for later camera/AI; keep only for simple tests. |
| 6 | Raspberry Pi-3 | Pi3 Model B | 3 | POSSIBLE | Can prototype basic GPIO/sensors, but Pi 4 is a better available base. |
| 7 | Respberry pi4 B | Model B | 20 | USE | Best inventory computer for V1–V3. |
| 8 | WiFi-LE (small) | ESP8266EX | 4 | OPTIONAL | Not needed because the Pi already provides networking. |
| 9 | WiFi-Module | ESP8266 | 100 | OPTIONAL | Can act as a network peripheral, but not preferred for motor control. |
| 10 | GSM-800L (small) | SIM800L | 4 | NOT NEEDED | No cellular connectivity requirement. |
| 11 | GSM-900A | SIM900A | 21 | NOT NEEDED | No cellular connectivity requirement. |
| 12 | Bluetooth-LE | CC2541 | 4 | OPTIONAL | Not required; USB/Wi-Fi is simpler for this build. |
| 13 | Bluetooth-Module | HC05 | 38 | OPTIONAL | Could be used for a simple remote-control experiment, not needed in core build. |
| 14 | BB Shield | SYB170 | 4 | OPTIONAL | Only if compatible with your chosen Arduino prototype. |
| 15 | XBee-Module | S2/S2C | 47 | NOT NEEDED | No need for a separate radio link in the core build. |
| 16 | Xbee-Shield-Arduino | Arduino | 17 | NOT NEEDED | Only relevant if using XBee modules. |
| 17 | Xbee-Shield-USB | USB | 20 | NOT NEEDED | Only relevant if using XBee modules. |
| 18 | GPS-Module | NEO6M | 50 | NOT NEEDED | GPS is inappropriate for a desk-scale indoor robot. |
| 19 | TFT-Touch-2.4 | SPFD5408 | 5 | USE IN V2 | Candidate face/eyes display. |
| 20 | LCD-20x4 | JHD204A | 10 | OPTIONAL | Useful for debug/status, not needed once TFT/dashboard exists. |
| 21 | LCD-16x2 | JHD162A | 30 | OPTIONAL | Useful for debug/status, not needed once TFT/dashboard exists. |
| 22 | L293D-4-Motor Board | L293D | 15 | POSSIBLE SUBSTITUTE | Can prototype motors, but L298N/TB6612 is preferable for the final small robot. |
| 23 | L293D-2-Motor Board | L293D | 17 | POSSIBLE SUBSTITUTE | Can prototype motors, but L298N/TB6612 is preferable for the final small robot. |
| 24 | L298-2-Motor Board | L298N | 26 | USE IN V1 | Best inventory motor-driver option for a first prototype; later swap to TB6612FNG. |
| 25 | PIR Sensor | BISS0001 | 49 | NOT NEEDED | Detects motion, not suitable as the primary desk obstacle sensor. |
| 26 | Ultrasonic Sensor | HCRS04 | 112 | USE IN V1 | Temporary obstacle range sensor; replace/augment with ToF for compact final design. |
| 27 | Tmp-Hum Sensor | DHT11 | 18 | NOT NEEDED | Environmental sensing is outside the MVP. |
| 28 | Soil Mst Sensor | LM393 | 28 | NOT NEEDED | Not relevant. |
| 29 | Raindrop Sensor | LM393 | 15 | NOT NEEDED | Not relevant. |
| 30 | Sound Sensor | LM386 | 52 | NOT A MIC | Not suitable as the V2 speech microphone; buy a USB mic. |
| 31 | Load Sensor | HX711 | 8 | NOT NEEDED | Could be a future experiment, not needed for core robot. |
| 32 | JoyStick | KY023 | 9 | OPTIONAL | Can be a manual controller/debug input, but terminal is the requested interface. |
| 33 | RFID Reader | RC522 | 9 | OPTIONAL FUTURE | Could support tagged-object interactions later. |
| 34 | RFID-TAG |  | 104 | OPTIONAL FUTURE | Potential future desk-object identification. |
| 35 | RFID-Key Chain |  | 11 | OPTIONAL FUTURE | Potential future tagged interaction. |
| 36 | Flame Sensor |  | 5 | NOT NEEDED | No fire detection requirement. |
| 37 | MQ-5 Sensor |  | 12 | NOT NEEDED | Gas sensing outside scope. |
| 38 | MQ-7 Sensor |  | 18 | NOT NEEDED | Gas sensing outside scope. |
| 39 | MQ-8 Sensor |  | 10 | NOT NEEDED | Gas sensing outside scope. |
| 40 | MQ-9 Sensor |  | 10 | NOT NEEDED | Gas sensing outside scope. |
| 41 | MQ-2 Sensor |  | 21 | NOT NEEDED | Gas sensing outside scope. |
| 42 | MQ-6 Sensor |  | 10 | NOT NEEDED | Gas sensing outside scope. |
| 43 | MQ-4 Sensor |  | 11 | NOT NEEDED | Gas sensing outside scope. |
| 44 | MQ-3Sensor |  | 15 | NOT NEEDED | Gas sensing outside scope. |
| 45 | MQ-135 Sensor |  | 13 | NOT NEEDED | Gas sensing outside scope. |
| 46 | Servo Motor | 996R,9g | 30 | USE IN V2 | Available actuators for small arm joints; verify torque and voltage for your mechanism. |
| 47 | IR Sensor |  | 180 | USE IN V1 | Preferred inventory option for downward desk-edge detection. |
| 48 | Stepper Motor |  | 5+10 | NOT PREFERRED | Not needed for the mobile base; adds driver/control complexity. |
| 49 | Meggnetic Switch sensor |  | 5 | OPTIONAL FUTURE | Could be used for a physical lid/position sensor, but not required. |
| 50 | LDR Light sensor |  | 5 | NOT NEEDED | Not required for core robot. |
| 51 | LORO IOT kits |  | 5 | NOT NEEDED | Not required. |
| 52 | LORA IOT TRAINER KIT(L-IOT) |  | 8 | NOT NEEDED | Not required for a single desk robot. |
| 53 | VGA CAMARA MODULE | OV7670 | 5 | PROTOTYPE ONLY | Can validate camera capture, but not the recommended final camera path. |
| 54 | VIB SENSOR |  | 4 | NOT NEEDED | Not required. |
| 55 | MPU6050 |  | 40 | USE IN V1-3 | Available IMU for rough yaw/turn feedback; BNO085/086 is the stronger upgrade. |